## Compliance Requirements
Requirement ID | Requirement | Department | Control Area | Compliance Status | Priority | Last Reviewed | Next Review Due | Owner | Evidence / Notes | Gap Description | Corrective Action Status
CR001 | Access permissions reviewed | IT | Access Control | Compliant | Low | 2026-01-12 | 2026-04-12 | IT Manager | Quarterly access review evidence stored | No gap identified | Closed
CR002 | Employee data access restricted | HR | Data Protection | Compliant | Low | 2026-01-15 | 2026-04-15 | HR Manager | Role-based access list approved | No gap identified | Closed
CR003 | Customer records retained according to policy | Operations | Records Management | Gap Identified | High | 2026-02-01 | 2026-05-01 | Operations Lead | Retention schedule not consistently applied | Document and implement retention schedule | Open
CR004 | Staff complete annual compliance training | HR | Training | Compliant | Low | 2026-01-20 | 2026-04-20 | HR Manager | Training completion report available | No gap identified | Closed
CR005 | Multi-factor authentication enabled for privileged accounts | IT | Cybersecurity | Gap Identified | High | 2026-02-10 | 2026-05-10 | IT Manager | Some privileged accounts lack MFA | Enable MFA and verify all privileged accounts | Under Review
CR006 | Incident response plan tested annually | IT | Incident Management | In Progress | Medium | 2026-03-01 | 2026-06-01 | Security Analyst | Tabletop exercise scheduled | Exercise not yet completed | In Progress
CR007 | Customer complaints logged and resolved within SLA | Operations | Customer Operations | Compliant | Medium | 2026-01-25 | 2026-04-25 | Operations Lead | Complaint register and SLA report reviewed | No gap identified | Closed
CR008 | Third-party vendors assessed before onboarding | Finance | Third-Party Risk | Gap Identified | Medium | 2026-02-05 | 2026-05-05 | Procurement Lead | Vendor risk assessment missing for two vendors | Complete risk assessments for outstanding vendors | Open
CR009 | Financial reconciliations completed monthly | Finance | Financial Controls | Compliant | Medium | 2026-01-31 | 2026-04-30 | Finance Manager | Signed reconciliation samples available | No gap identified | Closed
CR010 | Data backups tested and recovery documented | IT | Business Continuity | Compliant | High | 2026-02-15 | 2026-05-15 | IT Manager | Backup restoration test passed | No gap identified | Closed
CR011 | Privacy notices provided at customer data collection | Operations | Data Protection | Gap Identified | High | 2026-02-18 | 2026-05-18 | Data Protection Lead | Some collection forms use an outdated notice | Update forms and confirm notice version | Under Review
CR012 | Conflicts of interest declared and reviewed | HR | Ethics | Compliant | Medium | 2026-01-28 | 2026-04-28 | Compliance Officer | Annual declarations recorded | No gap identified | Closed
CR013 | Regulatory changes assessed and assigned to owners | Finance | Regulatory Monitoring | In Progress | High | 2026-03-10 | 2026-06-10 | Compliance Officer | New guidance review underway | Impact assessment and owner assignment pending | In Progress
CR014 | Sensitive files encrypted at rest | IT | Cybersecurity | Compliant | High | 2026-02-22 | 2026-05-22 | Security Analyst | Encryption settings verified | No gap identified | Closed
CR015 | Records of processing activities maintained | Operations | Data Governance | Gap Identified | Medium | 2026-02-25 | 2026-05-25 | Data Protection Lead | Processing inventory has incomplete owners | Complete inventory and assign owners | Open
CR016 | Expense approvals follow delegated authority limits | Finance | Financial Controls | Compliant | Medium | 2026-02-28 | 2026-05-28 | Finance Manager | Sample approvals within policy limits | No gap identified | Closed
CR017 | Business continuity contacts reviewed | Operations | Business Continuity | In Progress | Medium | 2026-03-12 | 2026-06-12 | Operations Lead | Contact review is underway | Confirm current contacts and test escalation | In Progress
CR018 | Security patches applied within defined timelines | IT | Cybersecurity | Compliant | High | 2026-03-15 | 2026-06-15 | IT Manager | Patch compliance report meets target | No gap identified | Closed
CR019 | Customer identity checks documented | Operations | Customer Due Diligence | Compliant | High | 2026-03-18 | 2026-06-18 | Operations Lead | Sample customer files contain required checks | No gap identified | Closed
CR020 | Compliance evidence stored in approved repository | Finance | Evidence Management | Compliant | Low | 2026-03-20 | 2026-06-20 | Compliance Officer | Evidence links verified for sampled requirements | No gap identified | Closed

## Corrective Actions
Action ID | Requirement ID | Corrective Action | Department | Priority | Action Owner | Action Status | Target Date | Action Notes
CA001 | CR003 | Implement records retention schedule | Operations | High | Operations Lead | Open | 2026-11-15 | Create approved schedule, map record types, and brief process owners.
CA002 | CR005 | Enable MFA for privileged accounts | IT | High | IT Manager | Under Review | 2026-11-05 | Identify remaining accounts, enforce MFA, and retain verification evidence.
CA003 | CR008 | Complete vendor risk assessments | Finance | Medium | Procurement Lead | Open | 2026-11-20 | Collect assessments for outstanding vendors and record approval decisions.
CA004 | CR011 | Update privacy notices on collection forms | Operations | High | Data Protection Lead | Under Review | 2026-11-10 | Confirm approved notice wording and replace outdated versions across forms.
CA005 | CR015 | Complete processing inventory and assign owners | Operations | Medium | Data Protection Lead | Open | 2026-11-25 | Fill missing inventory fields and assign accountable business owners.
CA006 | CR006 | Run annual incident response exercise | IT | Medium | Security Analyst | In Progress | 2026-12-05 | Run tabletop exercise, document findings, and track follow-up actions.
CA007 | CR013 | Complete regulatory change impact assessment | Finance | High | Compliance Officer | In Progress | 2026-11-30 | Document impact, assign owners, and agree implementation deadlines.
CA008 | CR017 | Review business continuity contact list | Operations | Medium | Operations Lead | In Progress | 2026-11-18 | Validate contacts and test escalation route.

## Read Me
Field | Details
Project | Project 2: Compliance Gap Analysis & Monitoring Dashboard
Organisation | ClearPath Financial Services Ltd. (fictional portfolio scenario)
Purpose | Track compliance requirements, identify gaps, and monitor corrective actions.
Dataset note | Synthetic practice data created for a portfolio project; not real company or customer data.
Status counts | 20 requirements: 12 Compliant, 5 Gap Identified, 3 In Progress, 0 Not Assessed.
Priority note | Priorities describe relative urgency; confirm with a real risk assessment in real-world use.